## Sheet2
Project Name: Healthify
Major tasks
Responsible | Shiva Rama Krishna | Sowmya | Swaroopa | Vineetha | Anshitha | Total Estimated Hours
Sprint 1 - RFP
1.1 User Stories | 1 | 1 | 3 | 3 | 1 | 9
1.3 ER Diagram | 3 | 1 | 2 | 2 | 2 | 10
1.3 Cost Estimation | 2 | 2 | 2 | 1 | 3 | 10
1.4 Proposed Screens | 1 | 3 | 1 | 2 | 2 | 9
1.5 Schedule Management | 2 | 1 | 2 | 2 | 3 | 10
48
Sprint 2 - User Development
2.1 User UI development | 2 | 2 | 1 | 3 | 2 | 10
2.2 User Database Design | 3 | 2 | 2 | 1 | 3 | 11
2.3 User Implementation | 3 | 1 | 4 | 2 | 2 | 12
2.4 User Deploy | 2 | 2 | 3 | 2 | 3 | 12
45
Sprint 3 - Admin Development
3.1 Admin UI development | 2 | 4 | 3 | 2 | 3 | 14
3.2 Admin Database Design | 1 | 1 | 1 | 3 | 2 | 8
3.3 Admin Implementation | 3 | 2 | 3 | 2 | 3 | 13
3.4 Admin Deploy | 1 | 1 | 2 | 3 | 1 | 8
43
Sprint 4 - Admin Web Develop
4.1 Admin webpage UI | 2 | 3 | 2 | 2 | 1 | 10
4.2 Admin BackEnd | 2 | 2 | 1 | 3 | 2 | 10
4.3 Admin Implementation | 1 | 2 | 2 | 2 | 2 | 9
4.4 Admin Deploy | 2 | 2 | 1 | 2 | 3 | 10
39
Total | 33 | 36 | 35 | 35 | 35 | 175